## Sheet1
Task | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | BREAK | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | EXAMS
Project Proposal
Apply for Human Ethics Approval
Produce biblography of grounded theory studies
Contact sampling groups
Write preliminary report
Write presentation
Submit preliminary report
Presentation
Collect data by the form of interviews
Open code all of the collected data | bar: W15 to W16
Selective code the data | bar: W17 to W21
Write theoretical notes/memos | bar: W15 to W21
Sort the theoretical notes/memos | bar: W22 to W24
Draft final report | bar: W25 to W27
Write presentation | bar: W28 to W29
Review report
Submit report
Presentation