## Sheet1
Task | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | BREAK | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Project Proposal
Apply for Human Ethics Approval
Produce summaries of similar studies
Pilot Study
Outline the interview questions
Contact sampling groups
Write preliminary report
Write presentation
Submit preliminary report
Presentation
Collect data by the form of interviews
Open code all of the collected data | bar: 18
Selective code the data | bar: 19 to 25
Write theoretical notes/memos | bar: 18 to 25
Sort the theoretical notes/memos | bar: 26 to 28
Draft final report | bar: 28 to 30
Write presentation | bar: 31 to 33
Review report | bar: 33 to 34
Submit report | bar: 34
Presentation | bar: 35